## Migration Plan
| Activity Plan For Mobile Application Development | Start | End |  | Greeny Home - Mobile Web Application Development Plan
| Target Time Lines | 2016-09-20 | 2016-11-18
[5 empty] | 2016-09-24 | [6 empty] | 2016-10-01 | [30 empty] | 2016-11-01 | [29 empty] | 2016-12-01 | [30 empty] | 2017-01-01 | [30 empty] | 2017-02-01 | [27 empty] | 2017-03-01 | [30 empty] | 2017-04-01
 | time axis 2016-09-24 to 2017-04-07
|  | Planned Start Date | Planned End Date | % Compl.
Requirement Analysis
1 | Use case analysis, interviews and selection of a use case | 2016-09-20 | 2016-09-22 | 100%
2 | Develop and design paper based wire frames | 2016-09-20 | 2016-09-22 | 100%
3 | Develop flow chart for the design | 2016-09-22 | 2016-09-24 | 100%
4 | Evaluation and selection of prototyping tools | 2016-09-22 | 2016-09-24 | 100%
5 | Research and investigate the android & iOS app differences | 2016-09-22 | 2016-09-24 | 100%
Design Proto Type
1 | Develop the layout of the design(UXPin) | 2016-09-26 | 2016-09-30 | 100%
3 | Test the design using the design tool | 2016-09-26 | 2016-09-30 | 100%
4 | Perform user freed back for prototype | 2016-09-29 | 2016-10-03 | 100%
5 | Evaluate the feed back(Team & External Users) | 2016-09-29 | 2016-10-03 | 100%
6 | Adapt the changes based on end user feed back | 2016-10-02 | 2016-10-04 | 100%
7 | Review and finalize the documentation | 2016-10-05 | 2016-10-05 | 100%
Development of mobile web application
1 | Develop Web Application | 2016-10-09 | 2016-11-11 | 20%
2 | Testing and quality assuarance | 2016-11-01 | 2016-11-14 | 0%
3 | Review and finalize the implemenation | 2016-11-06 | 2016-11-17 | 0%
2 | Lesson Learned & project closure | 2016-11-13 | 2016-11-18 | 0%

## Data Sheet (hidden)
Project Plan Master Data Sheet
Member List | Status | Priority
Axway/kavindra | open | High
Staple/Arnstein | closed | Low
Staple/Fredrik | Ongoing | Medium